## Sheet
Sheet Name | Description
J23-0064-ITC-006-01 | ZS.540: Hose Enclosure - Slide Door Closed
J23-0064-ITC-006-02 | ZS.541: Hose Enclosure - Front Left Door Closed
J23-0064-ITC-006-03 | ZS.542: Hose Enclosure - Front Right Door Closed
J23-0064-ITC-006-04 | FSL.315: pH Controller - Low Flow Alarm

## J23-0064-ITC-006-01
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Hose Enclosure - Slide Door Closed |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Digital Input
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [ZS.540] Input Off |  | Trigger Field Device to ON | [ZS540] Input ON
2 | [ZS.540] Input On |  | Trigger Field Device to OFF | [ZS540] Input OFF
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-006-02
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Hose Enclosure - Front Left Door Closed |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Digital Input
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [ZS.541] Input Off |  | Trigger Field Device to ON | [ZS541] Input ON
2 | [ZS.541] Input On |  | Trigger Field Device to OFF | [ZS541] Input OFF
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-006-03
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Hose Enclosure - Front Right Door Closed |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Digital Input
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [ZS.542] Input Off |  | Trigger Field Device to ON | [ZS542] Input ON
2 | [ZS.542] Input On |  | Trigger Field Device to OFF | [ZS542] Input OFF
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-006-04
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | pH Controller - Low Flow Alarm |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Digital Input
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [FSL.315] Input Off |  | Trigger Field Device to ON | [FSL315] Input ON
2 | [FSL.315] Input On |  | Trigger Field Device to OFF | [FSL315] Input OFF
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed: