## Sheet
Sheet Name | Description
J23-0064-ITC-005-01 | AT.GS01A: Hose Treatment Enclosure - Unsafe Red
J23-0064-ITC-005-02 | AT.GS01B: Hose Treatment Enclosure - Safe Green
J23-0064-ITC-005-03 | AT.GS01C: Process Alarm - Control Panel Traffic Light Orange

## J23-0064-ITC-005-01
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Hose Treatment Enclosure - Unsafe Red |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Digital Output
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [AT.GS01A] Output Off |  | [AT_521A_Run] set to 0 | [R0/S5/Ch12] Output Off [Red Panel Light is off]
2 | [AT.GS01A] Output On |  | [AT_521A_Run] set to 1 | [R0/S5/Ch12] Output On [Red Panel Light is Activated]
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-005-02
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Hose Treatment Enclosure - Safe Green |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Digital Output
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [AT.GS01B] Output Off |  | [AT_521B_Run] set to 0 | [R0/S5/Ch13] Output Off [Green Panel Light is off]
2 | [AT.GS01B] Output On |  | [AT_521B_Run] set to 1 | [R0/S5/Ch13] Output On [Green Panel Light is On]
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-005-03
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Process Alarm - Control Panel Traffic Light Orange |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Digital Output
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [AT.GS01C] Output Off |  | [AT_521C_Run] set to 0 | [R0/S5/Ch14] Output Off [Amber Panel Light is off]
2 | [AT.GS01C] Output On |  | [AT_521C_Run] set to 1 | [R0/S5/Ch14] Output On [Amber Panel Light is on]
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed: