## Sheet
Sheet Name | Description
J23-0064-ITC-001-01 | CA_32_01: SO2 Vapouriser
J23-0064-ITC-001-02 | CA_32_02: Air Preheater
J23-0064-ITC-001-03 | CA_39_03A: SO2/SO3 Converter Heater A
J23-0064-ITC-001-04 | CA_39_03B: SO2/SO3 Converter Heater B
J23-0064-ITC-001-05 | CA_32_04: NH3 Vapouriser
J23-0064-ITC-001-06 | NH3_21_01: NH3 Scrubber Transfer Pump
J23-0064-ITC-001-07 | NH3_22_01: NH3 Scrubber Blower
J23-0064-ITC-001-08 | SO2_22_01: SO2 Scrubber Blower
J23-0064-ITC-001-09 | WW_21_01: Wastewater Transfer Pump

## J23-0064-ITC-001-01
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | SO2 Vapouriser |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [CA_32_01] Auto Start | [CA_32_01]_Ready = 1 [CA_32_01]_Fault = 0 All trip inactive | Set PLC tag [CA_32_01] _cmd_AutOn = 1 | [CA_32_01] Run command bit = 1 ([IO_ADDRESS]) [CA_32_01] starts
2 | [CA_32_01] Drive Trip - Prevents Run | [CA_32_01]_Ready = 0 [CA_32_01]_Fault = 0 All trips inactive | Set PLC tag [CA_32_01] _cmd_AutOn = 1 | [CA_32_01] Run command bit = 0 ([IO_ADDRESS]) [CA_32_01] doesn't start
3 | [CA_32_01] Drive Error - Prevents Run | [CA_32_01]_Ready = 1 [CA_32_01]_Fault = 1 All trips inactive | Set PLC tag [CA_32_01] _cmd_AutOn = 1 | [CA_32_01] Run command bit = 0 ([IO_ADDRESS]) [CA_32_01] doesn't start
4 | [CA_32_01] Interlock - Prevents Run | [CA_32_01]_Ready = 1 [CA_32_01]_Fault = 0 [Any Trip] = 1 | Set PLC tag [CA_32_01] _cmd_AutOn = 1 | [CA_32_01] Run command bit = 0 ([IO_ADDRESS]) [CA_32_01] doesn't start
5 | Emergency Stop | [CA_32_01]_Running indication = 1 | Press E-Stop Button | [CA_32_01]_Ready = 0 [CA_32_01]_Fault = 1 [CA_32_01] stops
6 | [CA_32_01] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [CA_32_01] _cmd_AutOn = 1 | [CA_32_01] Run command bit = 1 ([IO_ADDRESS]) [CA_32_01] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-02
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Air Preheater |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [CA_32_02] Auto Start | [CA_32_02]_Ready = 1 [CA_32_02]_Fault = 0 All trip inactive | Set PLC tag [CA_32_02] _cmd_AutOn = 1 | [CA_32_02] Run command bit = 1 ([IO_ADDRESS]) [CA_32_02] starts
2 | [CA_32_02] Drive Trip - Prevents Run | [CA_32_02]_Ready = 0 [CA_32_02]_Fault = 0 All trips inactive | Set PLC tag [CA_32_02] _cmd_AutOn = 1 | [CA_32_02] Run command bit = 0 ([IO_ADDRESS]) [CA_32_02] doesn't start
3 | [CA_32_02] Drive Error - Prevents Run | [CA_32_02]_Ready = 1 [CA_32_02]_Fault = 1 All trips inactive | Set PLC tag [CA_32_02] _cmd_AutOn = 1 | [CA_32_02] Run command bit = 0 ([IO_ADDRESS]) [CA_32_02] doesn't start
4 | [CA_32_02] Interlock - Prevents Run | [CA_32_02]_Ready = 1 [CA_32_02]_Fault = 0 [Any Trip] = 1 | Set PLC tag [CA_32_02] _cmd_AutOn = 1 | [CA_32_02] Run command bit = 0 ([IO_ADDRESS]) [CA_32_02] doesn't start
5 | Emergency Stop | [CA_32_02]_Running indication = 1 | Press E-Stop Button | [CA_32_02]_Ready = 0 [CA_32_02]_Fault = 1 [CA_32_02] stops
6 | [CA_32_02] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [CA_32_02] _cmd_AutOn = 1 | [CA_32_02] Run command bit = 1 ([IO_ADDRESS]) [CA_32_02] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-03
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | SO2/SO3 Converter Heater A |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [CA_39_03A] Auto Start | [CA_39_03A]_Ready = 1 [CA_39_03A]_Fault = 0 All trip inactive | Set PLC tag [CA_39_03A] _cmd_AutOn = 1 | [CA_39_03A] Run command bit = 1 ([IO_ADDRESS]) [CA_39_03A] starts
2 | [CA_39_03A] Drive Trip - Prevents Run | [CA_39_03A]_Ready = 0 [CA_39_03A]_Fault = 0 All trips inactive | Set PLC tag [CA_39_03A] _cmd_AutOn = 1 | [CA_39_03A] Run command bit = 0 ([IO_ADDRESS]) [CA_39_03A] doesn't start
3 | [CA_39_03A] Drive Error - Prevents Run | [CA_39_03A]_Ready = 1 [CA_39_03A]_Fault = 1 All trips inactive | Set PLC tag [CA_39_03A] _cmd_AutOn = 1 | [CA_39_03A] Run command bit = 0 ([IO_ADDRESS]) [CA_39_03A] doesn't start
4 | [CA_39_03A] Interlock - Prevents Run | [CA_39_03A]_Ready = 1 [CA_39_03A]_Fault = 0 [Any Trip] = 1 | Set PLC tag [CA_39_03A] _cmd_AutOn = 1 | [CA_39_03A] Run command bit = 0 ([IO_ADDRESS]) [CA_39_03A] doesn't start
5 | Emergency Stop | [CA_39_03A]_Running indication = 1 | Press E-Stop Button | [CA_39_03A]_Ready = 0 [CA_39_03A]_Fault = 1 [CA_39_03A] stops
6 | [CA_39_03A] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [CA_39_03A] _cmd_AutOn = 1 | [CA_39_03A] Run command bit = 1 ([IO_ADDRESS]) [CA_39_03A] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-04
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | SO2/SO3 Converter Heater B |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [CA_39_03B] Auto Start | [CA_39_03B]_Ready = 1 [CA_39_03B]_Fault = 0 All trip inactive | Set PLC tag [CA_39_03B] _cmd_AutOn = 1 | [CA_39_03B] Run command bit = 1 ([IO_ADDRESS]) [CA_39_03B] starts
2 | [CA_39_03B] Drive Trip - Prevents Run | [CA_39_03B]_Ready = 0 [CA_39_03B]_Fault = 0 All trips inactive | Set PLC tag [CA_39_03B] _cmd_AutOn = 1 | [CA_39_03B] Run command bit = 0 ([IO_ADDRESS]) [CA_39_03B] doesn't start
3 | [CA_39_03B] Drive Error - Prevents Run | [CA_39_03B]_Ready = 1 [CA_39_03B]_Fault = 1 All trips inactive | Set PLC tag [CA_39_03B] _cmd_AutOn = 1 | [CA_39_03B] Run command bit = 0 ([IO_ADDRESS]) [CA_39_03B] doesn't start
4 | [CA_39_03B] Interlock - Prevents Run | [CA_39_03B]_Ready = 1 [CA_39_03B]_Fault = 0 [Any Trip] = 1 | Set PLC tag [CA_39_03B] _cmd_AutOn = 1 | [CA_39_03B] Run command bit = 0 ([IO_ADDRESS]) [CA_39_03B] doesn't start
5 | Emergency Stop | [CA_39_03B]_Running indication = 1 | Press E-Stop Button | [CA_39_03B]_Ready = 0 [CA_39_03B]_Fault = 1 [CA_39_03B] stops
6 | [CA_39_03B] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [CA_39_03B] _cmd_AutOn = 1 | [CA_39_03B] Run command bit = 1 ([IO_ADDRESS]) [CA_39_03B] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-05
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | NH3 Vapouriser |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [CA_32_04] Auto Start | [CA_32_04]_Ready = 1 [CA_32_04]_Fault = 0 All trip inactive | Set PLC tag [CA_32_04] _cmd_AutOn = 1 | [CA_32_04] Run command bit = 1 ([IO_ADDRESS]) [CA_32_04] starts
2 | [CA_32_04] Drive Trip - Prevents Run | [CA_32_04]_Ready = 0 [CA_32_04]_Fault = 0 All trips inactive | Set PLC tag [CA_32_04] _cmd_AutOn = 1 | [CA_32_04] Run command bit = 0 ([IO_ADDRESS]) [CA_32_04] doesn't start
3 | [CA_32_04] Drive Error - Prevents Run | [CA_32_04]_Ready = 1 [CA_32_04]_Fault = 1 All trips inactive | Set PLC tag [CA_32_04] _cmd_AutOn = 1 | [CA_32_04] Run command bit = 0 ([IO_ADDRESS]) [CA_32_04] doesn't start
4 | [CA_32_04] Interlock - Prevents Run | [CA_32_04]_Ready = 1 [CA_32_04]_Fault = 0 [Any Trip] = 1 | Set PLC tag [CA_32_04] _cmd_AutOn = 1 | [CA_32_04] Run command bit = 0 ([IO_ADDRESS]) [CA_32_04] doesn't start
5 | Emergency Stop | [CA_32_04]_Running indication = 1 | Press E-Stop Button | [CA_32_04]_Ready = 0 [CA_32_04]_Fault = 1 [CA_32_04] stops
6 | [CA_32_04] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [CA_32_04] _cmd_AutOn = 1 | [CA_32_04] Run command bit = 1 ([IO_ADDRESS]) [CA_32_04] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-06
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | NH3 Scrubber Transfer Pump |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [NH3_21_01] Auto Start | [NH3_21_01]_Ready = 1 [NH3_21_01]_Fault = 0 All trip inactive | Set PLC tag [NH3_21_01] _cmd_AutOn = 1 | [NH3_21_01] Run command bit = 1 ([IO_ADDRESS]) [NH3_21_01] starts
2 | [NH3_21_01] Drive Trip - Prevents Run | [NH3_21_01]_Ready = 0 [NH3_21_01]_Fault = 0 All trips inactive | Set PLC tag [NH3_21_01] _cmd_AutOn = 1 | [NH3_21_01] Run command bit = 0 ([IO_ADDRESS]) [NH3_21_01] doesn't start
3 | [NH3_21_01] Drive Error - Prevents Run | [NH3_21_01]_Ready = 1 [NH3_21_01]_Fault = 1 All trips inactive | Set PLC tag [NH3_21_01] _cmd_AutOn = 1 | [NH3_21_01] Run command bit = 0 ([IO_ADDRESS]) [NH3_21_01] doesn't start
4 | [NH3_21_01] Interlock - Prevents Run | [NH3_21_01]_Ready = 1 [NH3_21_01]_Fault = 0 [Any Trip] = 1 | Set PLC tag [NH3_21_01] _cmd_AutOn = 1 | [NH3_21_01] Run command bit = 0 ([IO_ADDRESS]) [NH3_21_01] doesn't start
5 | Emergency Stop | [NH3_21_01]_Running indication = 1 | Press E-Stop Button | [NH3_21_01]_Ready = 0 [NH3_21_01]_Fault = 1 [NH3_21_01] stops
6 | [NH3_21_01] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [NH3_21_01] _cmd_AutOn = 1 | [NH3_21_01] Run command bit = 1 ([IO_ADDRESS]) [NH3_21_01] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-07
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | NH3 Scrubber Blower |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [NH3_22_01] Auto Start | [NH3_22_01]_Ready = 1 [NH3_22_01]_Fault = 0 All trip inactive | Set PLC tag [NH3_22_01] _cmd_AutOn = 1 | [NH3_22_01] Run command bit = 1 ([IO_ADDRESS]) [NH3_22_01] starts
2 | [NH3_22_01] Drive Trip - Prevents Run | [NH3_22_01]_Ready = 0 [NH3_22_01]_Fault = 0 All trips inactive | Set PLC tag [NH3_22_01] _cmd_AutOn = 1 | [NH3_22_01] Run command bit = 0 ([IO_ADDRESS]) [NH3_22_01] doesn't start
3 | [NH3_22_01] Drive Error - Prevents Run | [NH3_22_01]_Ready = 1 [NH3_22_01]_Fault = 1 All trips inactive | Set PLC tag [NH3_22_01] _cmd_AutOn = 1 | [NH3_22_01] Run command bit = 0 ([IO_ADDRESS]) [NH3_22_01] doesn't start
4 | [NH3_22_01] Interlock - Prevents Run | [NH3_22_01]_Ready = 1 [NH3_22_01]_Fault = 0 [Any Trip] = 1 | Set PLC tag [NH3_22_01] _cmd_AutOn = 1 | [NH3_22_01] Run command bit = 0 ([IO_ADDRESS]) [NH3_22_01] doesn't start
5 | Emergency Stop | [NH3_22_01]_Running indication = 1 | Press E-Stop Button | [NH3_22_01]_Ready = 0 [NH3_22_01]_Fault = 1 [NH3_22_01] stops
6 | [NH3_22_01] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [NH3_22_01] _cmd_AutOn = 1 | [NH3_22_01] Run command bit = 1 ([IO_ADDRESS]) [NH3_22_01] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-08
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | SO2 Scrubber Blower |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [SO2_22_01] Auto Start | [SO2_22_01]_Ready = 1 [SO2_22_01]_Fault = 0 All trip inactive | Set PLC tag [SO2_22_01] _cmd_AutOn = 1 | [SO2_22_01] Run command bit = 1 ([IO_ADDRESS]) [SO2_22_01] starts
2 | [SO2_22_01] Drive Trip - Prevents Run | [SO2_22_01]_Ready = 0 [SO2_22_01]_Fault = 0 All trips inactive | Set PLC tag [SO2_22_01] _cmd_AutOn = 1 | [SO2_22_01] Run command bit = 0 ([IO_ADDRESS]) [SO2_22_01] doesn't start
3 | [SO2_22_01] Drive Error - Prevents Run | [SO2_22_01]_Ready = 1 [SO2_22_01]_Fault = 1 All trips inactive | Set PLC tag [SO2_22_01] _cmd_AutOn = 1 | [SO2_22_01] Run command bit = 0 ([IO_ADDRESS]) [SO2_22_01] doesn't start
4 | [SO2_22_01] Interlock - Prevents Run | [SO2_22_01]_Ready = 1 [SO2_22_01]_Fault = 0 [Any Trip] = 1 | Set PLC tag [SO2_22_01] _cmd_AutOn = 1 | [SO2_22_01] Run command bit = 0 ([IO_ADDRESS]) [SO2_22_01] doesn't start
5 | Emergency Stop | [SO2_22_01]_Running indication = 1 | Press E-Stop Button | [SO2_22_01]_Ready = 0 [SO2_22_01]_Fault = 1 [SO2_22_01] stops
6 | [SO2_22_01] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [SO2_22_01] _cmd_AutOn = 1 | [SO2_22_01] Run command bit = 1 ([IO_ADDRESS]) [SO2_22_01] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-001-09
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Wastewater Transfer Pump |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
Drive
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [WW_21_01] Auto Start | [WW_21_01]_Ready = 1 [WW_21_01]_Fault = 0 All trip inactive | Set PLC tag [WW_21_01] _cmd_AutOn = 1 | [WW_21_01] Run command bit = 1 ([IO_ADDRESS]) [WW_21_01] starts
2 | [WW_21_01] Drive Trip - Prevents Run | [WW_21_01]_Ready = 0 [WW_21_01]_Fault = 0 All trips inactive | Set PLC tag [WW_21_01] _cmd_AutOn = 1 | [WW_21_01] Run command bit = 0 ([IO_ADDRESS]) [WW_21_01] doesn't start
3 | [WW_21_01] Drive Error - Prevents Run | [WW_21_01]_Ready = 1 [WW_21_01]_Fault = 1 All trips inactive | Set PLC tag [WW_21_01] _cmd_AutOn = 1 | [WW_21_01] Run command bit = 0 ([IO_ADDRESS]) [WW_21_01] doesn't start
4 | [WW_21_01] Interlock - Prevents Run | [WW_21_01]_Ready = 1 [WW_21_01]_Fault = 0 [Any Trip] = 1 | Set PLC tag [WW_21_01] _cmd_AutOn = 1 | [WW_21_01] Run command bit = 0 ([IO_ADDRESS]) [WW_21_01] doesn't start
5 | Emergency Stop | [WW_21_01]_Running indication = 1 | Press E-Stop Button | [WW_21_01]_Ready = 0 [WW_21_01]_Fault = 1 [WW_21_01] stops
6 | [WW_21_01] Restart | Emergency Stop test completed immediately prior. | Trip Reset Activated on HMI Set PLC tag [WW_21_01] _cmd_AutOn = 1 | [WW_21_01] Run command bit = 1 ([IO_ADDRESS]) [WW_21_01] starts
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed: