## Sheet
Sheet Name | Description
J23-0064-ITC-008-01 | Trip.100: Process Trip
J23-0064-ITC-008-02 | Trip.101: SO2 Converter Trip
J23-0064-ITC-008-03 | Trip.500: Emergency Stop Activated

## J23-0064-ITC-008-01
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Process Trip |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
9
Trips
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [Trip.100] Activate Condition 1 | [Trip.100] Not Active [TT144 High High] is Off | Operate [TT144 High High] | [Trip.100] Active
2 | [Trip.100] Activate Condition 2 | [Trip.100] Not Active [PT152 High High] is Off | Operate [PT152 High High] | [Trip.100] Active
3 | [Trip.100] Activate Condition 3 | [Trip.100] Not Active [FT156 High High] is Off | Operate [FT156 High High] | [Trip.100] Active
4 | [Trip.100] Activate Condition 4 | [Trip.100] Not Active [TT159 High High] is Off | Operate [TT159 High High] | [Trip.100] Active
5 | [Trip.100] Activate Condition 5 | [Trip.100] Not Active [PDT181 Low Low] is Off | Operate [PDT181 Low Low] | [Trip.100] Active
6 | [Trip.100] Activate Condition 6 | [Trip.100] Not Active [SO2 Scrubber Motor stopped during sequence] is Off | Operate [SO2 Scrubber Motor stopped during sequence] | [Trip.100] Active
7 | [Trip.100] Activate Condition 7 | [Trip.100] Not Active [TT244 High High] is Off | Operate [TT244 High High] | [Trip.100] Active
8 | [Trip.100] Activate Condition 8 | [Trip.100] Not Active [PT252 High High] is Off | Operate [PT252 High High] | [Trip.100] Active
9 | [Trip.100] Activate Condition 9 | [Trip.100] Not Active [FT256 High High] is Off | Operate [FT256 High High] | [Trip.100] Active
10 | [Trip.100] Activate Condition 10 | [Trip.100] Not Active [TT144 High High0] is Off | Operate [TT144 High High0] | [Trip.100] Active
11 | [Trip.100] Activate Condition 11 | [Trip.100] Not Active [TT144 High High1] is Off | Operate [TT144 High High1] | [Trip.100] Active
12 | [Trip.100] Activate Condition 12 | [Trip.100] Not Active [TT144 High High2] is Off | Operate [TT144 High High2] | [Trip.100] Active
13 | [Trip.100] Activate Condition 13 | [Trip.100] Not Active [TT144 High High3] is Off | Operate [TT144 High High3] | [Trip.100] Active
14 | [Trip.100] Activate Condition 14 | [Trip.100] Not Active [TT144 High High4] is Off | Operate [TT144 High High4] | [Trip.100] Active
15 | [Trip.100] Activate Condition 15 | [Trip.100] Not Active [TT144 High High5] is Off | Operate [TT144 High High5] | [Trip.100] Active
16 | [Trip.100] Activate Condition 16 | [Trip.100] Not Active [TT144 High High6] is Off | Operate [TT144 High High6] | [Trip.100] Active
17 | [Trip.100] Activate Condition 17 | [Trip.100] Not Active [TT144 High High7] is Off | Operate [TT144 High High7] | [Trip.100] Active
18 | [Trip.100] Activate Condition 18 | [Trip.100] Not Active [TT144 High High8] is Off | Operate [TT144 High High8] | [Trip.100] Active
19 | [Trip.100] Activate Condition 19 | [Trip.100] Not Active [TT144 High High9] is Off | Operate [TT144 High High9] | [Trip.100] Active
20 | [Trip.100] Activate Condition 20 | [Trip.100] Not Active [PT152 High High0] is Off | Operate [PT152 High High0] | [Trip.100] Active
21 | [Trip.100] Activate Condition 21 | [Trip.100] Not Active [PT152 High High1] is Off | Operate [PT152 High High1] | [Trip.100] Active
22 | [Trip.100] Action 1 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV150]
23 | [Trip.100] Action 2 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV151]
24 | [Trip.100] Action 3 | [Trip.100] Not Active | Activate [Trip.100] | [OPEN SV650]
25 | [Trip.100] Action 4 | [Trip.100] Not Active | Activate [Trip.100] | [OPEN 100% TIC115]
26 | [Trip.100] Action 5 | [Trip.100] Not Active | Activate [Trip.100] | [OPEN 100% FIC155]
27 | [Trip.100] Action 6 | [Trip.100] Not Active | Activate [Trip.100] | [OPEN HS673]
28 | [Trip.100] Action 7 | [Trip.100] Not Active | Activate [Trip.100] | [OPEN SV100]
29 | [Trip.100] Action 8 | [Trip.100] Not Active | Activate [Trip.100] | [OPEN SV651]
30 | [Trip.100] Action 9 | [Trip.100] Not Active | Activate [Trip.100] | [OPEN 100% FIC658]
31 | [Trip.100] Action 10 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1500]
32 | [Trip.100] Action 11 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1501]
33 | [Trip.100] Action 12 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1502]
34 | [Trip.100] Action 13 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1503]
35 | [Trip.100] Action 14 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1504]
36 | [Trip.100] Action 15 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1505]
37 | [Trip.100] Action 16 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1506]
38 | [Trip.100] Action 17 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1507]
39 | [Trip.100] Action 18 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1508]
40 | [Trip.100] Action 19 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1509]
41 | [Trip.100] Action 20 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1510]
42 | [Trip.100] Action 21 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1511]
43 | [Trip.100] Action 22 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1512]
44 | [Trip.100] Action 23 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1513]
45 | [Trip.100] Action 24 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1514]
46 | [Trip.100] Action 25 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1515]
47 | [Trip.100] Action 26 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1516]
48 | [Trip.100] Action 27 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1517]
49 | [Trip.100] Action 28 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1518]
50 | [Trip.100] Action 29 | [Trip.100] Not Active | Activate [Trip.100] | [CLOSE SV1519]
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-008-02
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | SO2 Converter Trip |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
9
Trips
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [Trip.101] Activate Condition 1 | [Trip.101] Not Active [TT159 High High] is Off | Operate [TT159 High High] | [Trip.101] Active
10 | [Trip.101] Activate Condition 10 | [Trip.101] Not Active [TT159 High High0] is Off | Operate [TT159 High High0] | [Trip.101] Active
11 | [Trip.101] Activate Condition 11 | [Trip.101] Not Active [TT159 High High1] is Off | Operate [TT159 High High1] | [Trip.101] Active
12 | [Trip.101] Activate Condition 12 | [Trip.101] Not Active [TT159 High High2] is Off | Operate [TT159 High High2] | [Trip.101] Active
13 | [Trip.101] Activate Condition 13 | [Trip.101] Not Active [TT159 High High3] is Off | Operate [TT159 High High3] | [Trip.101] Active
14 | [Trip.101] Activate Condition 14 | [Trip.101] Not Active [TT159 High High4] is Off | Operate [TT159 High High4] | [Trip.101] Active
15 | [Trip.101] Activate Condition 15 | [Trip.101] Not Active [TT159 High High5] is Off | Operate [TT159 High High5] | [Trip.101] Active
16 | [Trip.101] Activate Condition 16 | [Trip.101] Not Active [TT159 High High6] is Off | Operate [TT159 High High6] | [Trip.101] Active
17 | [Trip.101] Activate Condition 17 | [Trip.101] Not Active [TT159 High High7] is Off | Operate [TT159 High High7] | [Trip.101] Active
18 | [Trip.101] Activate Condition 18 | [Trip.101] Not Active [TT159 High High8] is Off | Operate [TT159 High High8] | [Trip.101] Active
19 | [Trip.101] Activate Condition 19 | [Trip.101] Not Active [TT159 High High9] is Off | Operate [TT159 High High9] | [Trip.101] Active
20 | [Trip.101] Activate Condition 20 | [Trip.101] Not Active [nan0] is Off | Operate [nan0] | [Trip.101] Active
21 | [Trip.101] Activate Condition 21 | [Trip.101] Not Active [nan1] is Off | Operate [nan1] | [Trip.101] Active
22 | [Trip.101] Action 1 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS655]
23 | [Trip.101] Action 2 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)]
31 | [Trip.101] Action 10 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6550]
32 | [Trip.101] Action 11 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6551]
33 | [Trip.101] Action 12 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6552]
34 | [Trip.101] Action 13 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6553]
35 | [Trip.101] Action 14 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6554]
36 | [Trip.101] Action 15 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6555]
37 | [Trip.101] Action 16 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6556]
38 | [Trip.101] Action 17 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6557]
39 | [Trip.101] Action 18 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6558]
40 | [Trip.101] Action 19 | [Trip.101] Not Active | Activate [Trip.101] | [STOP Air-PreHeater EHS6559]
41 | [Trip.101] Action 20 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)0]
42 | [Trip.101] Action 21 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)1]
43 | [Trip.101] Action 22 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)2]
44 | [Trip.101] Action 23 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)3]
45 | [Trip.101] Action 24 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)4]
46 | [Trip.101] Action 25 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)5]
47 | [Trip.101] Action 26 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)6]
48 | [Trip.101] Action 27 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)7]
49 | [Trip.101] Action 28 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)8]
50 | [Trip.101] Action 29 | [Trip.101] Not Active | Activate [Trip.101] | [STOP SO2 Converter Temperature Control (TIC159)9]
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed:

## J23-0064-ITC-008-03
J23-0064-ITC-009-01
|  |  | Commissioning |  | Revision: | A
|  |  | Emergency Stop Activated |  | Template: | ITC_Type
[5 empty] | Project: | MAC TLO HPU Upgrade
[5 empty] | Date: | 29/11/23
9
Trips
Test Number | Test Description | Pre-Requisites | Test Action | Expected Result | Pass | Comment
1 | [Trip.500] Activate Condition 1 | [Trip.500] Not Active [E/Stop Active] is Off | Operate [E/Stop Active] | [Trip.500] Active
10 | [Trip.500] Activate Condition 10 | [Trip.500] Not Active [E/Stop Active0] is Off | Operate [E/Stop Active0] | [Trip.500] Active
11 | [Trip.500] Activate Condition 11 | [Trip.500] Not Active [E/Stop Active1] is Off | Operate [E/Stop Active1] | [Trip.500] Active
12 | [Trip.500] Activate Condition 12 | [Trip.500] Not Active [E/Stop Active2] is Off | Operate [E/Stop Active2] | [Trip.500] Active
13 | [Trip.500] Activate Condition 13 | [Trip.500] Not Active [E/Stop Active3] is Off | Operate [E/Stop Active3] | [Trip.500] Active
14 | [Trip.500] Activate Condition 14 | [Trip.500] Not Active [E/Stop Active4] is Off | Operate [E/Stop Active4] | [Trip.500] Active
15 | [Trip.500] Activate Condition 15 | [Trip.500] Not Active [E/Stop Active5] is Off | Operate [E/Stop Active5] | [Trip.500] Active
16 | [Trip.500] Activate Condition 16 | [Trip.500] Not Active [E/Stop Active6] is Off | Operate [E/Stop Active6] | [Trip.500] Active
17 | [Trip.500] Activate Condition 17 | [Trip.500] Not Active [E/Stop Active7] is Off | Operate [E/Stop Active7] | [Trip.500] Active
18 | [Trip.500] Activate Condition 18 | [Trip.500] Not Active [E/Stop Active8] is Off | Operate [E/Stop Active8] | [Trip.500] Active
19 | [Trip.500] Activate Condition 19 | [Trip.500] Not Active [E/Stop Active9] is Off | Operate [E/Stop Active9] | [Trip.500] Active
20 | [Trip.500] Activate Condition 20 | [Trip.500] Not Active [nan0] is Off | Operate [nan0] | [Trip.500] Active
21 | [Trip.500] Activate Condition 21 | [Trip.500] Not Active [nan1] is Off | Operate [nan1] | [Trip.500] Active
22 | [Trip.500] Action 1 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS655]
23 | [Trip.500] Action 2 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)]
24 | [Trip.500] Action 3 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Vapouriser EHS161]
25 | [Trip.500] Action 4 | [Trip.500] Not Active | Activate [Trip.500] | [STOP NH3 Vapouriser EHS257]
26 | [Trip.500] Action 5 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Scrubber Fan EHS184]
27 | [Trip.500] Action 6 | [Trip.500] Not Active | Activate [Trip.500] | [STOP NH3 Scrubber Fan EHS284]
28 | [Trip.500] Action 7 | [Trip.500] Not Active | Activate [Trip.500] | [STOP NH3 Scrubber Transfer Pump EHS307]
29 | [Trip.500] Action 8 | [Trip.500] Not Active | Activate [Trip.500] | [Stop Wastewater Tank Transfer Pump EHS325]
31 | [Trip.500] Action 10 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6550]
32 | [Trip.500] Action 11 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6551]
33 | [Trip.500] Action 12 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6552]
34 | [Trip.500] Action 13 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6553]
35 | [Trip.500] Action 14 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6554]
36 | [Trip.500] Action 15 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6555]
37 | [Trip.500] Action 16 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6556]
38 | [Trip.500] Action 17 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6557]
39 | [Trip.500] Action 18 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6558]
40 | [Trip.500] Action 19 | [Trip.500] Not Active | Activate [Trip.500] | [STOP Air-PreHeater EHS6559]
41 | [Trip.500] Action 20 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)0]
42 | [Trip.500] Action 21 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)1]
43 | [Trip.500] Action 22 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)2]
44 | [Trip.500] Action 23 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)3]
45 | [Trip.500] Action 24 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)4]
46 | [Trip.500] Action 25 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)5]
47 | [Trip.500] Action 26 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)6]
48 | [Trip.500] Action 27 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)7]
49 | [Trip.500] Action 28 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)8]
50 | [Trip.500] Action 29 | [Trip.500] Not Active | Activate [Trip.500] | [STOP SO2 Converter Temperature Control (TIC158, TE157A, TE157B)9]
Inspection Passed Sign Off
Date:
Beyond Electrical Engineering |  | Name: |  | Signature:
Client |  | Name: |  | Signature:
Remarks or Remedial Action Required:
Remedial Action Completed: